Business Plan: Friends of Belle Isle Aquarium

January, 2008 - July, 2009

1.  Goal:  Governmental Relations: Advance a proposal to the City of Detroit for the reopening and operation of the Belle Isle Aquarium.

| Action | Start | End | Responsibility | Measurement |
| --- | --- | --- | --- | --- |
| 1.1 Create "prospects file” of key influential people based on previous contacts. Include directory, brief bio, description of interaction & dates of contacts with future strategy and another file of contacts for potential membership or committee assistance. Develop methods to update. | 3/08 | 10/08 | Executive Committee | Prospect files completed |
| 1.2 Determine which City relationship(s) need to be renewed. | 2/08 | 2/09 | Executive Committee | Contact list narrowed |
| 1.3 Contact City personnel for a status report, e.g. status of contract for care of koi, etc. | 2/08 | 6/08 | President | Status report obtained |
| 1.4 Follow-up with Penske staff to review business plan, feasibility of Aquarium reopening, etc. & request them to act as third party to help negotiate with City. | 4/08 | 4/08 | President | Penske follow-up made |
| 1.5 After Penske staff responds, arrange meeting with City to discuss & agree on plans for MOU for reopening BIA. Take necessary steps to forge “Memo of Understanding” (MOU) with City: - Appoint Ad Hoc Committee to draft letter of intent and MOU - Seek counsel and samples for creation of “MOU.” - Draft a letter of intent for City and submit to appropriate City officials for agreement. - Forward draft “MOU” to Board and final copy to City. | 5/08 | 12/08 | President | Meeting held |

2. Goal:  Partnership Building: Continue to cultivate relationships/partnerships with Belle Isle and other organizations with common goals and possible interest in reopening the Aquarium.

| Action | Start | End | Responsibility | Measurement |
| --- | --- | --- | --- | --- |
| 2.1 Allocate funds to become a member of Belle Isle organizations et al and join. | 2/08 | 3/08 & Ongoing | Board | Proof of Membership |
| 2.2 Review key stakeholders/organizations, .e.g. Island groups, Detroit Zoo, Metro Parks, corporate, city, residents, members, preservation, recreation, tourism, education, etc. and determine relationship building effort for each one. | 3/08 | 9/08 & Ongoing | EC with input from Board | Proof of relationship building effort |
| 2.3 Contact at least one new organization each month and report back to Board at every meeting using a standard agenda line item called “New Partners.” | 3/08 | 11/08 & Ongoing | Board – Led by Saperstein | At least 8 new partners contacted & Reported on spreadsheet |
| 2.4 Invite above named stakeholders/organizations to meet to discuss common goals; best ways to support, cooperate & communicate; & update on our plan to reopen the BI Aquarium. Provide each with a copy of the business plan and appropriate marketing materials. | 3/08 | 1/09 | Board Led by Saperstein | 6-8 meetings held with new partners |
| 2.5 Follow up with communication to contacts made with individuals & organizations, e.g., PR for newsletter, etc. what is appropriate for particular situation. | 3/08 | 5/09 | As assigned | Items posted in newsletter/web or other documents completed |
| 2.6 Coordinate at least 6 meetings with BI organizations, aka BI Alliance to work toward creation of BI Conservancy. | 1/08 | 6/09 | President | Meetings held |
| 2.7 Solicit and gather current letters of support from stakeholders, individuals & organizations. | 3/08 | 12/08 | Secretary/Board | Letters in file and on website |

3. Goal: Marketing: Improve Friends of BIA’s credibility as a positive organization capable of Aquarium stewardship. Action; Start; End; Responsibility; Measurement. 3.1a. Create a prospectus with history, board bios, strategic, marketing & business plans, photos, press kit, talking points, BIA awards, etc. 3.1b. Letters of support; 3/08 3/08; 5/08 12/08; Executive Committee; All parts of prospectus completed. 3.2 Prepare a Powerpoint presentation on the mission, history, importance & accomplishments of FOBIA.; 2/08; 4/08; Marketing Committee; Powerpoint completed. 3.3 Train & schedule speakers to present Powerpoint; 2/08; Ongoing; Marketing Committee; PP & presentations made. 3.4 Organize and conduct a comprehensive membership drive.; 6/08; 9/08; Ad hoc committee; 50-75 new members. 3.5 Review, revise & update organization, design, overall content and ownership of website. Make changes as recommended to and agreed upon by Board . Measure public usage at each Board meeting.; 5/08; 9/08; Marketing Committee; Website updated and converted as agreed upon. Usage increased.. 3.6 Appoint ad hoc committee to plan and initiate a regional marketing initiative.; 1/08; 6/08; Ad hoc Committee; Completion of marketing initiative. 4. Goal: Organizational & Fund Development: Secure & maintain sufficient resources to enable the Organization to administer and support activities and fundraising efforts to attain goal of reopening the Aquarium. Action; Start; End; Responsibility; Measurement. 4.1 Develop an 12 month budget for the period 1/1/08 – 12/31/08 based on funding priorities.; 2/08; 3/08; Treasurer, Finance Committee; Budget adopted b Board. 4.2 Identify revenue sources & methods & goals for securing them: Memberships – Membership Drive, Events, Website, Mailings Selling Merchandise – Events, Website Donations – Events, Website, Mailings, Direct Contact Grants – Research Sources, Make Application Fundraiser – Explore Need; 5/08; 10/08; Appropriate committees; Priorities established. 4.3 Plan another major fundraising event with a goal of netting a minimjm of $15,000 for the organization.; 6/08; 12/08; New ad hoc committee; Successful event. 4.4 Identify potential future long term expenditures: Corporate Expenses – Insurance, Memberships In other Organizations, Website, Consultants, etc. Committees – Education, Events, Marketing, etc. for Printing, Supplies, Merchandise, etc.; 4/08; 5/08; Treasurer, Finance Committee; Expenditures incorporated into budget and planning documents. 4.5 Review volunteer & prospect lists & make contacts for assistance with planned programs & activities.; 2/08; Ongoing; Executive Committee; Review completed as needed. 4.6 Contact knowledgeable professional, aquarists, AZA, consultant(s) to obtain necessary information re steps required leading up to “Re-Opening Day” of the “New Belle Isle Aquarium.”; 5/08; 7/08; Sweet; Contacts made & documented. Reported back to Board.. 4.7 Create a job description, work plan & plan for recruitment for college intern(s) for accomplishment of Friends of BIA goals & objectives.; 3/08; 6/08; Novacek; Intern start work...